## Sayfa2
Cemre NB67 / Wind Farms Service Ship
LDA
Technical Sea Trial Booklet Rev.0
4. Sea Trial Schedule | [8 empty] | Sea Trial Schedule Rev.2
No | SFI | Test Item | To Be Present |  |  | To Be Recorded/Followed | Responsible | Date | Start Time | Estimated Duration
|  |  | Class | Flag | Owner
1 |  | Departure from yard (Class and owner onboard) | [5 empty] | 2021-04-02 | 10:00
2 |  | Kick-off meeting | A | NA | A |  |  | 2021-04-02 | 14:00 | 30 mins
3 | - | Adjustments | NA | NA | NA | - | Commissioning Dept. | 2021-04-02 | 13:00 | ~ 2 day
4 | 154.18 | Deviation test of magnetic compass | R | NA | W | 067-005-154.18_Rev_0 | Quality Dept. | 2021-04-03 | 9:00 | 30 mins
5 | 154.17 | Navigational and communication equipments test | A | NA | W | 067-005-154.17_Rev_0 | Electricity Dept. | 2021-04-03 | 9:00 | 5 hours
6 | 154.34 | Pager system – Functional test | NA | NA | A | 067-005-154.34_Rev_0 | Electricity Dept. | 2021-04-03 | 9:30 | 1 hours
7 | 154.28 | Vibration monitoring system – Functional test | NA | NA | A | 067-005-154.28_Rev_0 | Electricity Dept. | 2021-04-03 | 11:00 | 30 mins
8 | 761.01 | Fresh water generator – Alarm and safety functional test | NA | NA | A | 067-005-761.01_Rev_0 | Commissioning Dept. | 2021-04-03 | 13:00 | 1 hours
9 | TBA | Evacuation test of a injured person on a stretcher from the engine control room | A | NA | W | TBA | Quality Dept. | 2021-04-03 | 15:00 | 1 hours
10 | - | HAT remaining items | A | NA | W | Remaining HAT procedures | Commissioning Dept. | 2021-04-04 | 9:00 | ~ 1 day
11 | 154.04 | Power management system – Operation test | A | NA | W | 067-005-154.04_Rev_0 | Electricity Dept. | 2021-04-05 | 9:00 | 2 hours
12 | 154.07 | Harmonic distortion measurements | A | NA | W | 067-005-154.07_Rev_0 | Electricity Dept. | 2021-04-05 | 11:00 | 3 hours
13 | 154.31 | Electric motors for tunnel thrusters – Operation test | A | NA | W | 067-005-154.31_Rev_0 | Electricity Dept. | 2021-04-05 | 15:00 | 1 hour
14 | 154.32 | Electric motor for retractable thruster – Operation test | A | NA | W | 067-005-154.32_Rev_0 | Electricity Dept. | 2021-04-05 | 16:00 | 1 hour
15 | 154.33 | Electric motors for azimuth thrusters – Operation test | A | NA | W | 067-005-154.33_Rev_0 | Electricity Dept. | 2021-04-05 | 17:00 | 1 hour
16 | 154.01 | Bow thrusters – Operation test | A | NA | W | 067-005-154.01_Rev_0 | Commissioning Dept. | 2021-04-05 | 19:00 | 1 hour
17 | 154.02 | Retractable thruster – Operation test | A | NA | W | 067-005-154.02_Rev_0 | Commissioning Dept. | 2021-04-05 | 20:00 | 1 hour
18 | 154.03 | Azimuth thrusters – Operation test | A | NA | W | 067-005-154.03_Rev_0 | Commissioning Dept. | 2021-04-05 | 21:00 | 2 hours
19 | 154.22 | AUT-UMS endurance test | A | NA | W | 067-005-154.22_Rev_0 | Electricity Dept. | 2021-04-06 | 0:00 | 8 hours
20 | 154.19 | Endurance test | A | NA | W | 067-005-154.19_Rev_0 | Electricity Dept.
21 | 155.01 | Noise measurements | R | NA | W | 067-005-155.01_Rev_0 | Quality Dept.
22 | 155.02 | Vibration measurements | R | NA | W | 067-005-155.02_Rev_0 | Quality Dept.
23 | 890.04 | Lux measurements | NA | NA | A | 067-005-890.04_Rev_0 | Quality Dept.
24 | 154.21 | Smoke test | A | NA | W | 067-005-154.21_Rev_0 | Quality Dept.
25 | 154.09 | Electrical plant temperature rise measurements | R | NA | W | 067-005-154.09_Rev_0 | Electricity Dept.
26 | 154.20 | Exhaust system temperature rise measurements | R | NA | W | 067-005-154.20_Rev_0 | Quality Dept.
27 | 154.36 | Piping system operation test during endurance test | A | NA | W | 067-005-154.36_Rev_0 | Commissioning Dept.
28 | TBA | Bridge maneuvering and safety test | A | NA | W | TBA | Quality Dept. | 2021-04-06 | 8:00 | 1 hour
29 | 154.10 | Steering test | A | NA | W | 067-005-154.10_Rev_0 | Quality Dept. | 2021-04-06 | 9:00 | 1 hour
30 | 154.11 | Emergency steering test | A | NA | W | 067-005-154.11_Rev_0 | Quality Dept. | 2021-04-06
31 | 154.13 | Crash stop test | A | NA | W | 067-005-154.13_Rev_0 | Quality Dept. | 2021-04-06 | 10:00 | 30 mins
32 | 154.14 | Turning circle test | A | NA | W | 067-005-154.14_Rev_0 | Quality Dept. | 2021-04-06 | 10:30 | 1.30 hour
33 | 154.12 | Aft speed maneuverability test | A | NA | W | 067-005-154.12_Rev_0 | Quality Dept. | 2021-04-06 | 13:00 | 30 mins
34 | 155.01 | Noise measurements (GA-PA scope) | R | NA | W | 067-005-155.01_Rev_0 | Quality Dept. | 2021-04-06 | 13:00 | 3 hours
35 | 154.15 | Anchoring test | A | NA | W | 067-005-154.15_Rev_0 | Commissioning Dept. | 2021-04-06 | 14:00 | 1 hour
36 | 154.16 | MOB boat lowering test | A | NA | W | 067-005-154.16_Rev_0 | Commissioning Dept. | 2021-04-06 | 15:00 | 1 hour
37 | 154.35 | Lifeboat lowering test | A | NA | W | 067-005-154.35_Rev_0 | Commissioning Dept. | 2021-04-06 | 16:00 | 1 hour
38 | 154.27 | Daughter craft lowering test | NA | NA | A | 067-005-154.27_Rev_0 | Commissioning Dept. | 2021-04-06 | 17:00 | 2 hours
39 | 154.29 | Speed test and FO consumption test | NA | NA | A | 067-005-154.29_Rev_0 | Quality Dept. | 2021-04-06 | 20:00 | 5 hours
40 | 154.23 | Deadship recovery test | A | NA | W | 067-005-154.23_Rev_0 | Electricity Dept. | 2021-04-07 | 1:00 | 1 hour
41 | 154.24 | Blackout test | A | NA | W | 067-005-154.24_Rev_0 | Electricity Dept. | 2021-04-07 | 2:00 | 30 mins
42 | - | DP Adjustment | NA | NA | NA | - | Commissioning Dept. | 2021-04-07 | 9:00 | 5 hours
43 | 156.01 | Dynamic positioning system test | A | NA | W | 067-005-156.01_Rev_0 | Electricity Dept. | 2021-04-07 | 15:00 | ~ 1 day
44 | 158.01 | FMEA test | A | NA | W | 067-005-158.01_Rev_0 | Quality Dept. | 2021-04-08 | 15:00 | ~ 2 days
45 |  | Closing meeting | A | NA | W |  |  | 2021-04-10 | 15:00 | 30 mins
46 |  | End of trial - Return to yard | [5 empty] | 2021-04-10 | 16:00