## Sayfa2
Cemre NB67 / Wind Farms Service Ship
LDA
|  |  |  | 5_NB67_SAT_Schedule_Rev_3.xlsx |  |  |  | Technical Sea Trial Booklet Rev.0
4. Sea Trial Schedule | [8 empty] | Sea Trial Schedule Rev.2
No | SFI | Test Item | To Be Present |  |  | To Be Recorded/Followed | Responsible | Date | Start Time | Estimated Duration
|  |  | Class | Flag | Owner
1 |  | Departure from yard (Class and owner onboard) | [5 empty] | 2021-04-02 | 10:00
2 |  | Kick-off meeting | A | NA | A |  |  | 2021-04-02 | 14:00 | 30 mins
3 | - | Adjustments | NA | NA | NA | - | Commissioning Dept. | 2021-04-02 | 13:00 | ~ 2 day
| 761.02 | Reverse osmosis plant - Alarm and safety functional test | [6 empty] | 16:00
Ballast system - Operation test
Bilge system - Operation test
Sludge system - Operation test
Fire pumps - Operation test
Emergency stop system - Functional test
4 | 154.18 | Deviation test of magnetic compass | R | NA | W | 067-005-154.18_Rev_0 | Quality Dept. | 2021-04-03 | 9:00 | 30 mins
38 | 154.27 | Daughter craft lowering test | NA | NA | A | 067-005-154.27_Rev_0 | Commissioning Dept. | 2021-04-06 | 17:00 | 2 hours
10 | - | HAT remaining items | A | NA | W | Remaining HAT procedures | Commissioning Dept. | 2021-04-04 | 9:00 | ~ 1 day
19 | 154.22 | AUT-UMS endurance test | A | NA | W | 067-005-154.22_Rev_0 | Electricity Dept. | 2021-04-06 | 0:00 | 8 hours
20 | 154.19 | Endurance test | A | NA | W | 067-005-154.19_Rev_0 | Electricity Dept.
21 | 155.01 | Noise measurements | R | NA | W | 067-005-155.01_Rev_0 | Quality Dept.
22 | 155.02 | Vibration measurements | R | NA | W | 067-005-155.02_Rev_0 | Quality Dept.
23 | 890.04 | Lux measurements | NA | NA | A | 067-005-890.04_Rev_0 | Quality Dept.
24 | 154.21 | Smoke test | A | NA | W | 067-005-154.21_Rev_0 | Quality Dept.
25 | 154.09 | Electrical plant temperature rise measurements | R | NA | W | 067-005-154.09_Rev_0 | Electricity Dept.
26 | 154.20 | Exhaust system temperature rise measurements | R | NA | W | 067-005-154.20_Rev_0 | Quality Dept.
27 | 154.36 | Piping system operation test during endurance test | A | NA | W | 067-005-154.36_Rev_0 | Commissioning Dept.
45 |  | Closing meeting | A | NA | W |  |  | 2021-04-10 | 15:00 | 30 mins
46 |  | End of trial - Return to yard | [5 empty] | 2021-04-10 | 16:00