## Sayfa2
Cemre NB70 / Fishing Vessel
ATLANTIC DAWN
Technical Sea Trial Booklet Rev.0
4. Sea Trial Schedule | [10 empty] | Sea Trial Schedule Rev.0
No | SFI | Test Item | To Be Present |  |  | Attandance |  | To Be Recorded/Followed | Responsible | Date | Start Time | Estimated Duration (Hours)
|  |  | Class | Flag | Owner | BV | Atlantic
1 | - | Departure from yard (Class and owner onboard) to safety zone | - | - | - | - | - | - | Captan | 2021-10-18 | 10:00 | 24:00
2 | - | Kick-off meeting | ü | NA | ü | All | All | - | Quality | 2021-10-18 | 10:00 | 0:30
3 | - | Adjustments for MAN | - | - | - | - | - | - | MAN | 2021-10-18 | 10:30 | 5:00
4 | 154.16 | Navigational and communication equipment test | A | NA | W | Surveyor 1 | Owner 1 | Dursun, Autopilot test burada yapılacak | Commissioning | 2021-10-18 | 11:00 | -
5 | 154.07 | Main Propulsion - Operation test | A | NA | W | Surveyor 2 | Owner 2 | Dursun | Commissioning | 2021-10-18 | 15:30 | 4:00
6 | 154.30 | Reduction gear - Operation test | A | NA | W | Surveyor 2 | Owner 2 | Dursun | Commissioning | 2021-10-18 | 19:30 | 3:00
7 | 154.29 | Main propulsion engine - Load reduction checks | A | NA | W | Surveyor 2 | Owner 2 | Dursun | Commissioning | 2021-10-18 | 22:30 | 1:00
8 | - | PTI&PTH Internal Test | - | - | - | - | - | - | BMA | 2021-10-18 | 23:30 | 1:00
9 | - | HSG - Functional test | A | NA | W | Surveyor 1 | Owner 1 | Dursun | Electricity | 2021-10-19 | 0:30 | 1:00
10 | 154.06 | Power management system (PMS) - Operation test | A | NA | W | Surveyor 1 | Owner 1 | Dursun | Electricity | 2021-10-19 | 1:30 | 3:00
#REF! | 154.18 | Deviation test of magnetic compass | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.18_Rev_0_Deviation_Test_Of_Magnetic_Compass | Commissioning | 2021-10-19 | 4:30 | 0:30
#REF! | 154.11 | Endurance test | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.11_Rev_0_Endurance_Test | Commissioning | 2021-10-19 | 5:00 | 4:00
#REF! | 154.22 | Smoke test | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.22_Rev_0_Smoke_Test | Quality
#REF! | 155.01 | Noise and vibration measurement | R | NA | A | Surveyor 2 | Owner 2 | Satın alma | Quality
#REF! | 155.01 | Lux measurements | NA | NA | A | - | Owner 2 | Satın alma | Quality
#REF! | 155.01 | PA/GA noise measurement | R | NA | W | Surveyor 2 | Owner 2 | MCK | Quality
#REF! | 154.23 | Piping system operation test during endurance test | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.23_Rev_0_Piping_System_Operation_Test_During_Endurance_Test | Commissioning
#REF! | 154.12 | Exhaust system - Surface temperature measurement | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.12_Rev_0_Exhaust_System_and_Electrical_Panel_Temperature_Measurement | Quality
#REF! | 154.31 | Total harmonic distortion measurement | A | NA | W | Surveyor 2 | Owner 2 | Dursun | Electricity
#REF! | 154.05 | Anchoring test | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.05_Rev_0_Anchoring_Test | Commissioning | 2021-10-19 | 9:00 | 2:00
#REF! | 154.14 | Mob boat lowering test | A | NA | W | Surveyor 2 | Owner 2 | 070-005-154.14_Rev_0_Mob_Boat_Lowering_Test | Commissioning | 2021-10-19 | 11:00 | 1:30
#REF! | - | Adjustment for BMA | - | - | - | - | - | - | BMA | 2021-10-19 | 12:30 | 4:00
#REF! | 154.06 | ME peak shaving | A | NA | W | Surveyor 1 | Owner 1 | Dursun, battery testi burada yapılacak | Commissioning | 2021-10-19 | 16:30 | 1:00
#REF! | 154.03 | Steering gear - Operation test | A | NA | W | Surveyor 1 | Owner 1 | 070-005-154.03_Rev_0_Steering_Gear_Operation_Test | Commissioning | 2021-10-19 | 17:30 | 1:00
#REF! | 154.04 | Emergency steering test | A | NA | W | Surveyor 1 | Owner 1 | 070-005-154.04_Rev_0_Emergency_Steering_Test | Commissioning | 2021-10-19 | 18:30 | 1:00
#REF! | 154.08 | Crash stop test | A | NA | W | Surveyor 1 | Owner 1 | 070-005-154.08_Rev_0_Crash_Stop_Test | Quality | 2021-10-19 | 19:30 | 1:00
#REF! | 154.24 | Bridge maneuvering and safety test | A | NA | W | Surveyor 1 | Owner 1 | 070-005-154.24_Rev_0_Bridge_Maneuvering_And_Safety_Test | Quality | 2021-10-19 | 20:30 | 1:00
#REF! | 154.21 | Navigation lights - Visibility test | A | NA | W | Surveyor 1 | Owner 1 | 070-005-154.21_Rev_0_Navigation_Lights_Visibility_Test | Quality | 2021-10-19 | 21:30 | 1:00
#REF! | - | Adjustments for Brunvoll | - | - | - | - | - | - | Brunvoll | 2021-10-19 | 22:30 | 2:00
#REF! | 154.02 | Tunnel thrusters - Operation test | A | NA | W | Surveyor 1 | Owner 1 | Dursun | Commissioning | 2021-10-20 | 0:30 | 2:00
#REF! | 154.01 | Speed test and fuel consumption test | NA | NA | A | - | Owner 2 | 070-005-154.01_Rev_0_Speed_Test | Quality | 2021-10-20 | 2:30 | 2:00
#REF! | 155.02 | Bollard pull test | NA | NA | A | - | Owner 2 | 070-005-155.02_Rev_0_Bollard_Pull_Test | Quality | 2021-10-20 | 4:30 | 8:00
#REF! | - | Closing meeting with BV | ü | NA | ü | All | All | - | All | 2021-10-20 | 12:30 | 0:30
#REF! | - | Yard adjustment | - | - | - | - | - | - | Commissioning | 2021-10-20 | 13:00 | 3:00
#REF! | 363.03 | RSW circulation system - Operation test | NA | NA | A | - | Owner 2 | HAT? | Commissioning | 2021-10-20 | 16:00 | 20:00
#REF! | 465.04 | Return water/Levelling system - Operation test | NA | NA | A | - | Owner 2 | HAT?
#REF! | 465.02 | Vacuum system - Operation test | NA | NA | A | - | Owner 1 | HAT?
#REF! | 465.06 | Fish transport system - Operation test | NA | NA | A | - | Owner 1 | HAT?
#REF! | 465.07 | Fish pump - Functional test | NA | NA | A | - | Owner 1 | HAT?
#REF! | - | End of trial - Return to yard | - | - | - | - | - | - | Captan | 2021-10-21 | 12:00 | 0:30
#REF! | - | Hot deflection and allignment checks | A | NA | W | Surveyor 1 | Owner 2 | Dursun | Commissioning | 2021-10-21 | 12:30 | -
Formulas:
Date = IF([Start Time]<[Start Time, row above], ([Date, row above]+1),([Date, row above]))
Date = IF([Start Time]<M9, (L9+1),(L9))