## Sayfa2
Cemre NB73 / Fishing Vessel
ATLANTIC DAWN
Technical Sea Trial Booklet Rev.0
5. Sea Trial Schedule | [10 empty] | Sea Trial Schedule Rev.2
No | SFI | Test Item | To Be Present |  |  | Attandance |  | To Be Recorded/Followed | Responsible | Date | Start Time | Estimated Duration (Hours)
|  |  | Class | Flag | Owner | BV | Atlantic
1 | - | Departure from yard (Class and owner onboard) to safety zone | - | - | - | - | - | - | Captan | 2022-06-20 | 13:00 | 24:00
2 | - | Kick-off meeting | ü | NA | ü | All | All | - | Quality | 2022-06-20 | 13:00 | 0:30
3 | - | Adjustments for MAN | - | - | - | - | - | - | MAN | 2022-06-20 | 13:30 | 5:00
4 | - | PTI&PTH Internal Test | - | - | - | - | - | - | BMA | 2022-06-20 | 19:30 | 1:00
5 | - | Peak shaving adjustment for BMA | - | - | - | - | - | - | BMA | 2022-06-20 | 18:30 | 4:00
6 | 154.16 | Navigational and communication equipment test | A | NA | W | Surveyor 1 | Owner 1 | 071_005_1.154.16_Rev_0_Navigation and comminication equipment | Quality | 2022-06-20 | 22:30 | -
7 | 154.06 | ME peak shaving(Incl. Aux gens-battery, ME-battery) | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.06_Rev_0_Power_Management_System_Operation_Test | Commissioning | 2022-06-20 | 22:30 | 1:00
8 | 154.07 | Main Propulsion - Operation test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.07_Rev_0_Main_Propulsion_Operation_Test | Commissioning | 2022-06-20 | 23:30 | 4:00
9 | 154.21 | Navigation lights - Visibility test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.21_Rev_0_Navigation_Lights_Visibility_Test | Quality | 2022-06-21 | 3:30 | 1:00
10 | 795.01 | Blackout test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-795.01_Rev_0_Blackout_Recovery_Test | Electricity | 2022-06-21 | 4:30 | 1:00
11 | 154.18 | Deviation test of magnetic compass | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.18_Rev_0_Deviation_Test_Of_Magnetic_Compass | Quality | 2022-06-21 | 5:30 | 0:30
12 | 154.30 | Reduction gear - Operation test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.30_Rev_0_Reduction_Gear_Operation_Test | Commissioning | 2022-06-21 | 6:00 | 3:00
13 | 154.29 | Main propulsion engine (Including Load reduction checks ) | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.29_Rev_0_Main_Propulsion_Engine_Load_Reduction_Checks_Test | Commissioning | 2022-06-21 | 9:00 | 1:00
14 | 154.06 | HSG Drive - Functional test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.06_Rev_0_Power_Management_System_Operation_Test | Electricity | 2022-06-21 | 10:00 | 3:00
15 | 154.06 | Power management system (PMS) - Operation test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.06_Rev_0_Power_Management_System_Operation_Test | Electricity | 2022-06-21 | 13:00 | 3:00
16 | 154.05 | Anchoring test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.05_Rev_0_Anchoring_Test | Quality | 2022-06-21 | 16:00 | 1:00
17 | 154.14 | Mob boat lowering test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.14_Rev_0_Mob_Boat_Lowering_Test | Quality | 2022-06-21 | 17:00 | 1:00
18 | - | Adjustments for Brunvoll | - | - | - | - | - | - | Brunvoll | 2022-06-21 | 18:00 | 2:00
19 | 154.02 | Tunnel thrusters - Operation test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.02_Tunnel_Thrusters_Operation_Test | Quality | 2022-06-21 | 20:00 | 2:00
20 | 154.11 | Endurance test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.11_Rev_0_Endurance_Test | Quality | 2022-06-21 | 22:00 | 4:00
21 | 154.11 | MON-SHAFT notation checks | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.11_Rev_0_Endurance_Test | Quality
22 | 155.01 | Noise and vibration measurement | R | NA | A | Surveyor 2 | Owner 2 | 071-005-155.01_Rev_0_Noise_and_Vibration_Measurement_Test | Quality
23 | 155.03 | Lux measurements | NA | NA | A | - | Owner 2 | 071-005-155.03_Rev_0_Lux_Measurement_Test | Quality
24 | 155.01 | GA noise measurement | R | NA | W | Surveyor 2 | Owner 2 | 071-005-155.01_Rev_0_Noise_and_Vibration_Measurement_Test | Quality
25 | 154.23 | Piping system operation test during endurance test | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.23_Rev_0_Piping_System_Operation_Test_During_Endurance_Test | Commissioning
26 | 154.12 | Exhaust system - Surface temperature measurement (incl. back pressure) | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.12_Rev_0_Exhaust_System_and_Electrical_Panel_Temperature_Measurement | Quality
27 | 154.11 | Astern Trial | A | NA | W | Surveyor 2 | Owner 2 | 071-005-154.11_Rev_0_Endurance_Test | Quality
28 | 895.01 | Emergency Lighting | A | NA | W | Surveyor 1 | Owner 1 | 071-005-895.01_Rev_0_Main and Emergency_Floodlights & Exterior Light_Functional test | Electricity | 2022-06-22 | 2:00 | 1:15
29 | 154.24 | Bridge maneuvering and safety test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.24_Rev_0_Bridge_Maneuvering_And_Safety_Test | Quality | 2022-06-22 | 3:15 | 1:00
30 | 154.01 | Speed test and fuel consumption test | A | NA | W | Surveyor 1 | Owner 2 | 071-005-154.01_Rev_0_Speed_Test | Quality | 2022-06-22 | 4:15 | 2:00
31 | 154.03 | Steering gear - Operation test | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.03_Rev_0_Steering_Gear_Operation_Test | Quality | 2022-06-22 | 6:15 | 1:00
32 | 154.08 | Crash stop test (Include stoppping test) | A | NA | W | Surveyor 1 | Owner 1 | 071-005-154.08_Rev_0_Crash_Stop_Test | Quality | 2022-06-22 | 7:15 | 1:00
33 | 363.03 | MMC Remaining Items | NA | NA | A | - | Owner 2 | - | Commissioning | 2022-06-22 | 8:15 | 23:00
34 | 154.31 | Total harmonic distortion measurement | A | NA | W | Surveyor 2 | Owner 2 | - | Electricity | 2022-06-23 | 7:15 | 1:00
35 | 155.02 | Bollard pull test | NA | NA | A | - | Owner 2 | 071-005-155.02_Rev_0_Bollard_Pull_Test | Quality | 2022-06-23 | 8:15 | 6:00
36 | - | Closing meeting with BV | ü | NA | ü | All | All | - | All | 2022-06-23 | 14:15 | 0:30
37 | - | End of trial - Return to yard | - | - | - | - | - | - | Captan | 2022-06-23 | 14:45 | 0:30
38 | 154.29 | Hot deflection | A | NA | W | Surveyor 1 | Owner 2 | 071-005-154.29_Rev_0_Main_Propulsion_Engine_Load_Reduction_Checks_Test | Commissioning | 2022-06-23 | 15:15 | -
Formulas:
Date = IF([Start Time]<[Start Time, row above], ([Date, row above]+1),([Date, row above]))
Date = IF([Start Time]<M8, (L8+1),(L8))